## Dashboard
Tracker — Jira Dashboard | [9 empty] | Metric | Count
[10 empty] | Completed | 206
TOTAL ITEMS | 262 | COMPLETED | 206 | REMAINING | 56 | PROGRESS | 78.6% | LATEST SCRUM | SCRUM-358 | Remaining | 56
Epic Key | Epic Name | Epic Status | Total Items | Done | Remaining | Progress %
SCRUM-3 | Reflection Tree | Done | 19 | 19 | 0 | 100%
SCRUM-1 | Learning Path | Done | 43 | 43 | 0 | 100%
SCRUM-8 | System design | In Progress | 37 | 32 | 5 | 86.49%
SCRUM-49 | UX/UI | In Progress | 82 | 61 | 21 | 74.39%
SCRUM-30 | TEST | In Progress | 14 | 6 | 8 | 42.86%
SCRUM-2 | Authentication | In Progress | 26 | 25 | 1 | 96.15%
SCRUM-6 | Recommendation | In Progress | 16 | 4 | 12 | 25%
SCRUM-7 | Social Learning | Done | 9 | 8 | 1 | 88.89%
SCRUM-58 | Deploy | In Progress | 12 | 8 | 4 | 66.67%
SCRUM-5 | Dashboards | To Do | 4 | 0 | 4 | 0%
Sprint Timeline Summary
Sprint | Total Items | Done | Remaining | Progress % | Status
SCRUM Sprint 1 | 85 | 85 | 0 | 100.0% | Completed
SCRUM Sprint 2 | 46 | 46 | 0 | 100.0% | Completed
SCRUM Sprint 3 | 124 | 75 | 49 | 60.5% | In Progress
SCRUM Sprint 4 | 7 | 0 | 7 | 0.0% | Not Started
100.0% (85/85)
100.0% (46/46)
60.5% (75/124)
0.0% (0/7)

## System design
Issue key | Summary | Issue Type | Status | Priority | Assignee | Created | Due date | Story Points | Sprint | Parent Key | Parent Summary
SCRUM-8 | System design | Epic | In Progress | Highest |  | 2025-11-17 | 2026-03-16
SCRUM-64 | Infrastructure Set | Task | Done | Medium | Thiraphat Panthong | 2025-12-16 | 2025-12-29 |  | SCRUM Sprint 1 | SCRUM-8 | System design
SCRUM-72 | AI-service Setup | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-17 |  |  | SCRUM Sprint 1 | SCRUM-64 | Infrastructure Set
SCRUM-71 | Frontend Setup | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-17 |  |  | SCRUM Sprint 1 | SCRUM-64 | Infrastructure Set
SCRUM-70 | Tech Stack Setup | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-17 |  |  | SCRUM Sprint 1 | SCRUM-64 | Infrastructure Set
SCRUM-69 | Backend Setup | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-17 |  |  | SCRUM Sprint 1 | SCRUM-64 | Infrastructure Set
SCRUM-68 | Set Docker Setup | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-17 |  |  | SCRUM Sprint 1 | SCRUM-64 | Infrastructure Set
SCRUM-45 | Database Design | Task | Done | Highest | Nattapat Suwansipaisan | 2025-11-17 | 2025-12-29 |  | SCRUM Sprint 1 | SCRUM-8 | System design
SCRUM-195 | Database table | Subtask | Done | Medium | Nattapat Suwansipaisan | 2025-12-25 | 2025-12-26 |  | SCRUM Sprint 1 | SCRUM-45 | Database Design
SCRUM-83 | ER Diagram | Subtask | Done | Medium | Nattapat Suwansipaisan | 2025-12-17 | 2025-12-29 |  | SCRUM Sprint 1 | SCRUM-45 | Database Design
SCRUM-78 | Connect to backend | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-17 | 2025-12-30 |  | SCRUM Sprint 1 | SCRUM-45 | Database Design
SCRUM-80 | Create Table | Subtask | Done | Medium | Nattapat Suwansipaisan | 2025-12-17 | 2025-12-29 |  | SCRUM Sprint 1 | SCRUM-45 | Database Design
SCRUM-89 | Search System Template | Task | Done | Medium | Thiraphat Panthong | 2025-12-17 | 2026-01-02 |  | SCRUM Sprint 1 | SCRUM-8 | System design
SCRUM-211 | Connect to Qdrant Database | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-29 | 2025-12-29 |  | SCRUM Sprint 1 | SCRUM-89 | Search System Template
SCRUM-107 | Ranking & Retrieval | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-17 | 2025-12-29 |  | SCRUM Sprint 1 | SCRUM-89 | Search System Template
SCRUM-104 | Tech Stack to use | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-17 | 2025-12-29 |  | SCRUM Sprint 1 | SCRUM-89 | Search System Template
SCRUM-102 | Preprocessing | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-17 | 2025-12-29 |  | SCRUM Sprint 1 | SCRUM-89 | Search System Template
SCRUM-212 | Embedding data | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-29 | 2026-01-01 |  | SCRUM Sprint 1 | SCRUM-89 | Search System Template
SCRUM-108 | Filtering | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-17 | 2026-01-02 |  | SCRUM Sprint 1 | SCRUM-89 | Search System Template
SCRUM-209 | Logs Design | Task | Done | Medium | Thiraphat Panthong | 2025-12-28 | 2026-01-30 |  | SCRUM Sprint 2 | SCRUM-8 | System design
SCRUM-292 | Re-Format Logs | Subtask | Done | Medium | Thiraphat Panthong | 2026-01-24 | 2026-01-30 |  | SCRUM Sprint 2 | SCRUM-209 | Logs Design
SCRUM-291 | Connect Logs to Backend | Subtask | Done | Medium | Thiraphat Panthong | 2026-01-24 | 2026-01-30 |  | SCRUM Sprint 2 | SCRUM-209 | Logs Design
SCRUM-290 | Tech Stack to Use | Subtask | Done | Medium | Thiraphat Panthong | 2026-01-24 | 2026-01-30 |  | SCRUM Sprint 2 | SCRUM-209 | Logs Design
SCRUM-286 | Integrate system (Deploy) | Task | Done | Medium | Thiraphat Panthong | 2026-01-23 | 2026-02-09 |  | SCRUM Sprint 2 | SCRUM-8 | System design
SCRUM-289 | Design Flow and Integrate to CI/CD | Subtask | Done | Medium | Thiraphat Panthong | 2026-01-24 | 2026-01-30 |  | SCRUM Sprint 2 | SCRUM-286 | Integrate system (Deploy)
SCRUM-288 | PoC for deploy | Subtask | Done | Medium | Thiraphat Panthong | 2026-01-23 | 2026-02-03 |  | SCRUM Sprint 2 | SCRUM-286 | Integrate system (Deploy)
SCRUM-46 | API Design | Task | In Progress | Highest |  | 2025-11-17 | 2026-03-16 |  | SCRUM Sprint 3 | SCRUM-8 | System design
SCRUM-202 | Learning Path Node Endpoint | Subtask | Done | Medium | Napadech | 2025-12-26 | 2026-01-05 |  | SCRUM Sprint 1 | SCRUM-46 | API Design
SCRUM-201 | Quiz Endpoint | Subtask | Done | Medium | Napadech | 2025-12-25 | 2026-01-05 |  | SCRUM Sprint 2 | SCRUM-46 | API Design
SCRUM-200 | Tree Node Endpoint | Subtask | Done | Medium | Nattapat Suwansipaisan | 2025-12-25 | 2026-01-05 |  | SCRUM Sprint 1 | SCRUM-46 | API Design
SCRUM-199 | Tree Endpoint | Subtask | Done | Medium | Nattapat Suwansipaisan | 2025-12-25 | 2026-01-05 |  | SCRUM Sprint 1 | SCRUM-46 | API Design
SCRUM-143 | Recommendation Endpoints | Subtask | Done | Medium | Napadech | 2025-12-18 | 2026-01-30 |  | SCRUM Sprint 2 | SCRUM-46 | API Design
SCRUM-142 | Lernnig path Endpoints | Subtask | Done | Medium | Napadech | 2025-12-18 | 2026-01-05 |  | SCRUM Sprint 1 | SCRUM-46 | API Design
SCRUM-141 | Search Endpoints | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-18 | 2026-01-05 |  | SCRUM Sprint 1 | SCRUM-46 | API Design
SCRUM-194 | PROFILE Endpoint | Subtask | In Progress | Medium | Amy Tripp | 2025-12-22 | 2026-03-06 |  | SCRUM Sprint 3 | SCRUM-46 | API Design
SCRUM-140 | Auth Endpoints | Subtask | In Progress | Medium | Nattapat Suwansipaisan | 2025-12-18 | 2026-01-28 |  | SCRUM Sprint 2 | SCRUM-46 | API Design
SCRUM-77 | Document | Subtask | In Progress | Medium | Napadech | 2025-12-17 | 2026-03-16 |  | SCRUM Sprint 3 | SCRUM-46 | API Design
SCRUM-217 | Dashboard Endpoint | Subtask | In Progress | Medium | Thiraphat Panthong | 2026-01-04 | 2026-03-06 |  | SCRUM Sprint 3 | SCRUM-46 | API Design

## UX-UI
Issue key | Summary | Issue Type | Status | Priority | Assignee | Created | Due date | Story Points | Sprint | Parent Key | Parent Summary
SCRUM-49 | UX/UI | Epic | In Progress | Highest |  | 2025-11-17 | 2026-04-05
SCRUM-181 | Component-Widget | Task | Done | Highest | Nutgritta Prasomthongsuk | 2025-12-20 | 2026-01-04 |  | SCRUM Sprint 1 | SCRUM-49 | UX/UI
SCRUM-186 | Components | Subtask | Done | Medium | Amy Tripp | 2025-12-21 |  |  | SCRUM Sprint 1 | SCRUM-181 | Component-Widget
SCRUM-185 | Buttons | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-21 |  |  | SCRUM Sprint 1 | SCRUM-181 | Component-Widget
SCRUM-184 | Theme And Color | Subtask | Done | Medium | Amy Tripp | 2025-12-21 |  |  | SCRUM Sprint 1 | SCRUM-181 | Component-Widget
SCRUM-183 | Typography | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-21 |  |  | SCRUM Sprint 1 | SCRUM-181 | Component-Widget
SCRUM-51 | Reflection Page Layout | Task | In Progress | Highest | Amy Tripp | 2025-11-17 | 2026-02-25 |  | SCRUM Sprint 3 | SCRUM-49 | UX/UI
SCRUM-81 | Create New Tree Form | Subtask | Done | High | Amy Tripp | 2025-12-17 | 2026-01-27 |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-92 | View Tree Information Page | Subtask | Done | High | Amy Tripp | 2025-12-17 | 2026-01-30 |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-87 | Tree Visualization | Subtask | Done | High | Amy Tripp | 2025-12-17 | 2026-01-21 |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-84 | Create Pop-Up | Subtask | Done | High | Amy Tripp | 2025-12-17 | 2026-01-27 |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-88 | Change Album Info Pop-Up | Subtask | Done | Medium | Amy Tripp | 2025-12-17 | 2026-01-30 |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-94 | Add Reflect Pop-Up | Subtask | Done | Medium | Amy Tripp | 2025-12-17 | 2026-01-30 |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-250 | View Album Information Page | Subtask | Done | Lowest | Amy Tripp | 2026-01-13 | 2026-01-30 |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-86 | How To Use Pop-Up | Subtask | Done | Low | Amy Tripp | 2025-12-17 | 2026-01-30 |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-85 | Edit Pop-Up | Subtask | Done | Medium | Amy Tripp | 2025-12-17 | 2026-01-30 |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-95 | Recommend Pop-Up | Subtask | Done | Low | Amy Tripp | 2025-12-17 | 2026-01-30 |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-96 | Detail Pop-Up | Subtask | Done | Low | Amy Tripp | 2025-12-17 | 2026-01-30 |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-300 | Warning Popup | Subtask | Done | Medium | Amy Tripp | 2026-01-28 | 2026-02-02 |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-299 | Calendar Popup | Subtask | Done | Medium | Amy Tripp | 2026-01-28 | 2026-02-02 |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-298 | Resume + Retrieve Popup | Subtask | Done | Medium | Amy Tripp | 2026-01-28 | 2026-02-02 |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-293 | Connect Backend URL | Subtask | Done | Lowest | Amy Tripp | 2026-01-27 | 2026-02-04 |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-346 | Business Logic for CRUD | Subtask | Done | High | Amy Tripp | 2026-02-18 |  |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-297 | Change Location Popup | Subtask | Done | Medium | Amy Tripp | 2026-01-28 |  |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-296 | Delete Popup | Subtask | Done | Low | Amy Tripp | 2026-01-28 |  |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-82 | Page Layout | Subtask | Done | Highest | Amy Tripp | 2025-12-17 | 2025-12-31 |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-75 | Component-Widget | Subtask | Done | Highest | Amy Tripp | 2025-12-17 | 2025-12-31 |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-347 | Flow Optimization | Subtask | To Do | Medium | Amy Tripp | 2026-02-18 |  |  | SCRUM Sprint 3 | SCRUM-51 | Reflection Page Layout
SCRUM-50 | Learning Path Page Layout | Task | In Progress | Highest | Nutgritta Prasomthongsuk | 2025-11-17 | 2026-02-25 |  | SCRUM Sprint 3 | SCRUM-49 | UX/UI
SCRUM-74 | Component-Widget | Subtask | Done | Highest | Nutgritta Prasomthongsuk | 2025-12-17 | 2026-01-09 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-155 | [S]Learning Paths Overview Page | Subtask | Done | Highest | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-06 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-168 | [T]Create Status Page | Subtask | Done | Highest | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-08 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-165 | [T]Learning Path Status | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-08 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-164 | [T]Learning Paths Overview Page | Subtask | Done | Highest | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-08 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-163 | [T]Learn & Create Tab | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-08 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-162 | [S]Learning Path Status | Subtask | Done | Highest | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-08 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-169 | [T]Create Learning Path(Input Detail) | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-11 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-175 | [T]Create Node (Plain) | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-28 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-174 | [T]Create Plain Path | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-28 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-172 | [T]Create Node (AI) | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-28 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-171 | [T]Nodes Overview Page | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-14 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-170 | [T]AI Node Review Page | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-14 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-179 | [T]Delete Node Popup | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-31 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-178 | [T]Save Draft Popup | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-31 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-177 | [T]Publish Popup | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-31 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-176 | [T]Edit Node (Plain) | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-31 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-167 | [T]Delete Popup | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-31 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-166 | [T]Edit Popup | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-01-31 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-160 | [S]Rating Popup | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-02-04 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-159 | [S]Completion Popup | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-02-04 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-158 | [S]Quiz Page | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-02-04 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-156 | [S]Learning Page | Subtask | Done | Highest | Nutgritta Prasomthongsuk | 2025-12-18 |  |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-330 | Connect Backend URL | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2026-02-14 | 2026-02-16 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-349 | Business Logic for CRUD | Subtask | Done | High | Nutgritta Prasomthongsuk | 2026-02-18 |  |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-173 | [T]Edit Node (AI) | Subtask | Done | Medium | Nutgritta Prasomthongsuk | 2025-12-18 |  |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-154 | [S&T]Search & Filter | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-18 |  |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-157 | [S]Comments | Subtask | To Do | Medium | Nutgritta Prasomthongsuk | 2025-12-18 | 2026-02-04 |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-350 | Flow Optization | Subtask | To Do | Medium | Nutgritta Prasomthongsuk | 2026-02-18 |  |  | SCRUM Sprint 3 | SCRUM-50 | Learning Path Page Layout
SCRUM-52 | Authentication Pages | Task | In Progress | High | Amy Tripp | 2025-11-17 | 2026-02-27 |  | SCRUM Sprint 3 | SCRUM-49 | UX/UI
SCRUM-294 | Refactor and Layout | Subtask | Done | Highest | Amy Tripp | 2026-01-27 | 2026-02-08 |  | SCRUM Sprint 3 | SCRUM-52 | Authentication Pages
SCRUM-295 | Connect Backend URL | Subtask | Done | Medium | Amy Tripp | 2026-01-27 | 2026-02-18 |  | SCRUM Sprint 3 | SCRUM-52 | Authentication Pages
SCRUM-344 | Business logic for forgot/reset password | Subtask | Done | Medium | Amy Tripp | 2026-02-18 |  |  | SCRUM Sprint 3 | SCRUM-52 | Authentication Pages
SCRUM-342 | Business logic for verify Email(OTP) | Subtask | Done | Medium | Amy Tripp | 2026-02-18 |  |  | SCRUM Sprint 3 | SCRUM-52 | Authentication Pages
SCRUM-341 | Business logic for login/register | Subtask | Done | Medium | Amy Tripp | 2026-02-18 |  |  | SCRUM Sprint 3 | SCRUM-52 | Authentication Pages
SCRUM-340 | Role selected | Subtask | Done | Medium | Amy Tripp | 2026-02-18 |  |  | SCRUM Sprint 3 | SCRUM-52 | Authentication Pages
SCRUM-338 | Business logic in frontend | Subtask | Done | High | Amy Tripp | 2026-02-17 |  |  | SCRUM Sprint 3 | SCRUM-52 | Authentication Pages
SCRUM-337 | Sign-up Layout | Subtask | Done | High | Amy Tripp | 2026-02-17 |  |  | SCRUM Sprint 3 | SCRUM-52 | Authentication Pages
SCRUM-336 | Login Layout | Subtask | Done | High | Amy Tripp | 2026-02-17 |  |  | SCRUM Sprint 3 | SCRUM-52 | Authentication Pages
SCRUM-348 | Flow Optimization | Subtask | Done | Medium | Thiraphat Panthong | 2026-02-18 | 2026-02-27 |  | SCRUM Sprint 3 | SCRUM-52 | Authentication Pages
SCRUM-345 | Business logic for Social Auth | Subtask | To Do | Medium | Thiraphat Panthong | 2026-02-18 | 2026-02-27 |  | SCRUM Sprint 3 | SCRUM-52 | Authentication Pages
SCRUM-343 | Business logic for "Remember me" | Subtask | To Do | Medium | Thiraphat Panthong | 2026-02-18 | 2026-02-27 |  | SCRUM Sprint 3 | SCRUM-52 | Authentication Pages
SCRUM-311 | Admin Page | Task | To Do | Medium | Thiraphat Panthong | 2026-02-07 | 2026-03-03 |  | SCRUM Sprint 3 | SCRUM-49 | UX/UI
SCRUM-329 | connect to backend | Subtask | To Do | Medium | Thiraphat Panthong | 2026-02-13 | 2026-03-20 |  | SCRUM Sprint 3 | SCRUM-311 | Admin Page
SCRUM-362 | Dashboard Monitor | Subtask | To Do | Medium | Thiraphat Panthong | 2026-03-04 | 2026-03-20 |  | SCRUM Sprint 3 | SCRUM-311 | Admin Page
SCRUM-312 | Design | Subtask | To Do | Medium | Thiraphat Panthong | 2026-03-04 | 2026-03-20 |  | SCRUM Sprint 3 | SCRUM-311 | Admin Page
SCRUM-57 | Home Page | Task | To Do | Low |  | 2025-11-17 | 2026-03-18 |  | SCRUM Sprint 3 | SCRUM-49 | UX/UI
SCRUM-53 | Dashboard Layout | Task | To Do | Medium | Amy Tripp | 2025-11-17 | 2026-03-18 |  | SCRUM Sprint 3 | SCRUM-49 | UX/UI
SCRUM-334 | Mission Design | Subtask | To Do | Medium | Amy Tripp | 2026-02-14 | 2026-03-20 |  | SCRUM Sprint 3 | SCRUM-53 | Dashboard Layout
SCRUM-333 | Admin Dashboard | Subtask | To Do | Medium | Amy Tripp | 2026-02-14 | 2026-03-20 |  | SCRUM Sprint 3 | SCRUM-53 | Dashboard Layout
SCRUM-332 | Student Dashboard | Subtask | To Do | Medium | Amy Tripp | 2026-02-14 | 2026-03-20 |  | SCRUM Sprint 3 | SCRUM-53 | Dashboard Layout
SCRUM-331 | Teacher Dashboard | Subtask | To Do | Medium | Amy Tripp | 2026-02-14 | 2026-03-20 |  | SCRUM Sprint 3 | SCRUM-53 | Dashboard Layout
SCRUM-56 | Landing Page | Task | To Do | Lowest |  | 2025-11-17 | 2026-03-31 |  | SCRUM Sprint 3 | SCRUM-49 | UX/UI
SCRUM-335 | In App | Subtask | To Do | Medium |  | 2026-02-14 |  |  | SCRUM Sprint 3 | SCRUM-56 | Landing Page
SCRUM-328 | Get to know App | Subtask | To Do | Medium |  | 2026-02-13 |  |  | SCRUM Sprint 3 | SCRUM-56 | Landing Page

## Reflection Tree
Issue key | Summary | Issue Type | Status | Priority | Assignee | Created | Due date | Story Points | Sprint | Parent Key | Parent Summary
SCRUM-3 | Reflection Tree | Epic | Done | Highest |  | 2025-11-17 | 2026-02-16
SCRUM-191 | Design Flow | Task | Done | Highest | Nattapat Suwansipaisan | 2025-12-22 | 2025-12-27 |  | SCRUM Sprint 1 | SCRUM-3 | Reflection Tree
SCRUM-13 | Reflection Entry | Task | Done | Highest | Nattapat Suwansipaisan | 2025-11-17 | 2026-01-06 |  | SCRUM Sprint 1 | SCRUM-3 | Reflection Tree
SCRUM-226 | Edit Reflection | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-04 | 2026-01-06 |  | SCRUM Sprint 1 | SCRUM-13 | Reflection Entry
SCRUM-225 | Create Reflection | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-04 | 2026-01-06 |  | SCRUM Sprint 1 | SCRUM-13 | Reflection Entry
SCRUM-224 | Delete Reflection | Subtask | Done | Highest | Nattapat Suwansipaisan | 2026-01-04 | 2026-01-06 |  | SCRUM Sprint 1 | SCRUM-13 | Reflection Entry
SCRUM-223 | Read Reflection | Subtask | Done | Highest | Nattapat Suwansipaisan | 2026-01-04 | 2026-01-06 |  | SCRUM Sprint 1 | SCRUM-13 | Reflection Entry
SCRUM-221 | Input/Output format | Subtask | Done | Highest | Nattapat Suwansipaisan | 2026-01-04 | 2026-01-06 |  | SCRUM Sprint 1 | SCRUM-13 | Reflection Entry
SCRUM-220 | Collect reflection | Subtask | Done | Highest | Nattapat Suwansipaisan | 2026-01-04 | 2026-01-06 |  | SCRUM Sprint 1 | SCRUM-13 | Reflection Entry
SCRUM-15 | AI Insight Analysis | Task | Done | Highest | Nattapat Suwansipaisan | 2025-11-17 | 2026-01-17 |  | SCRUM Sprint 1 | SCRUM-3 | Reflection Tree
SCRUM-230 | Few-Shot Learning | Subtask | Done | Highest | Nattapat Suwansipaisan | 2026-01-04 | 2026-01-11 |  | SCRUM Sprint 1 | SCRUM-15 | AI Insight Analysis
SCRUM-227 | Base Prompt Template | Subtask | Done | Highest | Nattapat Suwansipaisan | 2026-01-04 | 2026-01-11 |  | SCRUM Sprint 1 | SCRUM-15 | AI Insight Analysis
SCRUM-233 | Re-ranking | Subtask | Done | High | Nattapat Suwansipaisan | 2026-01-04 | 2026-01-11 |  | SCRUM Sprint 1 | SCRUM-15 | AI Insight Analysis
SCRUM-232 | Exception Handling & Retry Logic | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-04 | 2026-01-11 |  | SCRUM Sprint 1 | SCRUM-15 | AI Insight Analysis
SCRUM-231 | LLM Result Parser & Validator | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-04 | 2026-01-11 |  | SCRUM Sprint 1 | SCRUM-15 | AI Insight Analysis
SCRUM-229 | Send to GO | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-04 | 2026-01-13 |  | SCRUM Sprint 1 | SCRUM-15 | AI Insight Analysis
SCRUM-228 | LLM Output -> Schema | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-04 | 2026-01-13 |  | SCRUM Sprint 1 | SCRUM-15 | AI Insight Analysis
SCRUM-253 | Reflection Album | Task | Done | Medium | Nattapat Suwansipaisan | 2026-01-18 | 2026-01-20 |  | SCRUM Sprint 2 | SCRUM-3 | Reflection Tree
SCRUM-360 | Upload cover image | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-03-04 | 2026-03-09 |  | SCRUM Sprint 3 | SCRUM-253 | Reflection Album
SCRUM-238 | Solve Bug | Task | Done | Low | Nattapat Suwansipaisan | 2026-01-07 | 2026-02-09 |  | SCRUM Sprint 2 | SCRUM-3 | Reflection Tree
SCRUM-361 | Solve Bug & Optimize | Task | In Progress | Low | Nattapat Suwansipaisan | 2026-03-04 | 2026-03-09 |  | SCRUM Sprint 3 | SCRUM-3 | Reflection Tree
SCRUM-16 | Link to Knowledge Tree, Tree Visualization | Task | Done | Low | Nattapat Suwansipaisan | 2025-11-17 | 2026-02-16 |  | SCRUM Sprint 2 | SCRUM-3 | Reflection Tree

## Learning Path
Issue key | Summary | Issue Type | Status | Priority | Assignee | Created | Due date | Story Points | Sprint | Parent Key | Parent Summary
SCRUM-1 | Learning Path | Epic | Done | Highest |  | 2025-11-17 | 2026-02-16
SCRUM-193 | Design Flow | Task | Done | Highest | Thiraphat Panthong | 2025-12-22 | 2025-12-28 |  | SCRUM Sprint 1 | SCRUM-1 | Learning Path
SCRUM-189 | Search Learning Path | Task | Done | Medium | Thiraphat Panthong | 2025-12-22 | 2026-01-18 |  | SCRUM Sprint 1 | SCRUM-1 | Learning Path
SCRUM-208 | Search ranking | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-28 | 2026-01-01 |  | SCRUM Sprint 1 | SCRUM-189 | Search Learning Path
SCRUM-204 | Input/Output format | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-28 | 2026-01-01 |  | SCRUM Sprint 1 | SCRUM-189 | Search Learning Path
SCRUM-203 | Connect Qdrant (development) | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-28 | 2026-01-01 |  | SCRUM Sprint 1 | SCRUM-189 | Search Learning Path
SCRUM-215 | Use with real data | Subtask | Done | Medium | Thiraphat Panthong | 2026-01-03 | 2026-01-30 |  | SCRUM Sprint 1 | SCRUM-189 | Search Learning Path
SCRUM-207 | Business logic | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-28 | 2026-01-07 |  | SCRUM Sprint 1 | SCRUM-189 | Search Learning Path
SCRUM-206 | Connect Qdrant (Production) | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-28 | 2026-01-30 |  | SCRUM Sprint 1 | SCRUM-189 | Search Learning Path
SCRUM-205 | Embedding with real data | Subtask | Done | Medium | Thiraphat Panthong | 2025-12-28 | 2026-01-30 |  | SCRUM Sprint 1 | SCRUM-189 | Search Learning Path
SCRUM-55 | Collection Learning Path | Task | Done | Highest | Napadech | 2025-11-17 | 2026-01-06 |  | SCRUM Sprint 1 | SCRUM-1 | Learning Path
SCRUM-196 | Read Learning Path | Subtask | Done | Medium | Napadech | 2025-12-25 |  |  | SCRUM Sprint 1 | SCRUM-55 | Collection Learning Path
SCRUM-98 | Delete Learning Path | Subtask | Done | Medium | Napadech | 2025-12-17 |  |  | SCRUM Sprint 1 | SCRUM-55 | Collection Learning Path
SCRUM-93 | Collect Learning Path | Subtask | Done | Medium | Napadech | 2025-12-17 |  |  | SCRUM Sprint 1 | SCRUM-55 | Collection Learning Path
SCRUM-91 | Edit Learning Path | Subtask | Done | Medium | Napadech | 2025-12-17 |  |  | SCRUM Sprint 1 | SCRUM-55 | Collection Learning Path
SCRUM-90 | Create Learning Path | Subtask | Done | Medium | Napadech | 2025-12-17 |  |  | SCRUM Sprint 1 | SCRUM-55 | Collection Learning Path
SCRUM-9 | Path Generator | Task | Done | Highest | Napadech | 2025-11-17 | 2026-01-13 |  | SCRUM Sprint 1 | SCRUM-1 | Learning Path
SCRUM-100 | Plain Path | Subtask | Done | Medium | Napadech | 2025-12-17 | 2026-01-10 |  | SCRUM Sprint 1 | SCRUM-9 | Path Generator
SCRUM-99 | Example data | Subtask | Done | Medium | Napadech | 2025-12-17 | 2026-01-10 |  | SCRUM Sprint 1 | SCRUM-9 | Path Generator
SCRUM-248 | Send to GO | Subtask | Done | Medium | Napadech | 2026-01-08 | 2026-01-14 |  | SCRUM Sprint 1 | SCRUM-9 | Path Generator
SCRUM-247 | LLM Output -> Schema | Subtask | Done | Medium | Napadech | 2026-01-08 | 2026-01-13 |  | SCRUM Sprint 1 | SCRUM-9 | Path Generator
SCRUM-245 | LLM Result Parser & Validator | Subtask | Done | Medium | Napadech | 2026-01-08 | 2026-01-13 |  | SCRUM Sprint 1 | SCRUM-9 | Path Generator
SCRUM-244 | Exception Handling & Retry Logic | Subtask | Done | Medium | Napadech | 2026-01-08 | 2026-01-13 |  | SCRUM Sprint 1 | SCRUM-9 | Path Generator
SCRUM-243 | Similarity & Re-ranking | Subtask | Done | Medium | Napadech | 2026-01-08 | 2026-01-10 |  | SCRUM Sprint 1 | SCRUM-9 | Path Generator
SCRUM-242 | Base Prompt Template | Subtask | Done | Medium | Napadech | 2026-01-08 | 2026-01-10 |  | SCRUM Sprint 1 | SCRUM-9 | Path Generator
SCRUM-239 | Sample data | Task | Done | Medium | Thiraphat Panthong | 2026-01-07 | 2026-01-20 |  | SCRUM Sprint 1 | SCRUM-1 | Learning Path
SCRUM-240 | Cover learning path | Subtask | Done | Medium | Thiraphat Panthong | 2026-01-07 |  |  | SCRUM Sprint 1 | SCRUM-239 | Sample data
SCRUM-252 | Load into DB | Subtask | Done | Medium | Thiraphat Panthong | 2026-01-15 |  |  | SCRUM Sprint 1 | SCRUM-239 | Sample data
SCRUM-251 | Data JSON format | Subtask | Done | Medium | Thiraphat Panthong | 2026-01-14 |  |  | SCRUM Sprint 1 | SCRUM-239 | Sample data
SCRUM-115 | History System | Task | Done | Medium | Napadech | 2025-12-17 | 2026-01-19 |  | SCRUM Sprint 1 | SCRUM-1 | Learning Path
SCRUM-118 | Assessment & Performance | Subtask | Done | Medium | Napadech | 2025-12-17 | 2026-01-14 |  | SCRUM Sprint 1 | SCRUM-115 | History System
SCRUM-117 | Progression History | Subtask | Done | Medium | Napadech | 2025-12-17 | 2026-01-14 |  | SCRUM Sprint 1 | SCRUM-115 | History System
SCRUM-116 | Activity & Event | Subtask | Done | Medium | Napadech | 2025-12-17 | 2026-01-14 |  | SCRUM Sprint 1 | SCRUM-115 | History System
SCRUM-10 | Progress Visualization | Task | Done | Medium | Napadech | 2025-11-17 | 2026-01-19 |  | SCRUM Sprint 1 | SCRUM-1 | Learning Path
SCRUM-123 | State Persistence | Subtask | Done | Medium | Napadech | 2025-12-17 | 2026-01-19 |  | SCRUM Sprint 1 | SCRUM-10 | Progress Visualization
SCRUM-122 | Real-time Calculation Engine | Subtask | Done | Medium | Napadech | 2025-12-17 | 2026-01-19 |  | SCRUM Sprint 1 | SCRUM-10 | Progress Visualization
SCRUM-121 | Status Indicators | Subtask | Done | Medium | Napadech | 2025-12-17 | 2026-01-19 |  | SCRUM Sprint 1 | SCRUM-10 | Progress Visualization
SCRUM-120 | Time Remaining Estimate | Subtask | Done | Medium | Napadech | 2025-12-17 | 2026-01-19 |  | SCRUM Sprint 1 | SCRUM-10 | Progress Visualization
SCRUM-119 | Progress Bar (Percentage) | Subtask | Done | Medium | Napadech | 2025-12-17 | 2026-01-19 |  | SCRUM Sprint 1 | SCRUM-10 | Progress Visualization
SCRUM-11 | Resume System | Task | Done | Low | Napadech | 2025-11-17 | 2026-01-20 |  | SCRUM Sprint 1 | SCRUM-1 | Learning Path
SCRUM-113 | Multi-Device Syn | Subtask | Done | Medium | Napadech | 2025-12-17 | 2026-01-16 |  | SCRUM Sprint 1 | SCRUM-11 | Resume System
SCRUM-112 | Prepare consume for dashboard | Subtask | Done | Medium | Napadech | 2025-12-17 | 2026-01-16 |  | SCRUM Sprint 1 | SCRUM-11 | Resume System
SCRUM-110 | Module Tracking | Subtask | Done | Medium | Napadech | 2025-12-17 | 2026-01-16 |  | SCRUM Sprint 1 | SCRUM-11 | Resume System
SCRUM-109 | Last Played Marker | Subtask | Done | Medium | Napadech | 2025-12-17 | 2026-01-16 |  | SCRUM Sprint 1 | SCRUM-11 | Resume System
SCRUM-359 | Optimize | Task | In Progress | Low | Napadech | 2025-03-04 | 2026-03-13 |  | SCRUM Sprint 3 | SCRUM-1 | Learning Path
SCRUM-113 | Adapt with frontend | Subtask | In Progress | Medium | Napadech | 2025-03-04 | 2026-03-13 |  | SCRUM Sprint 3 | SCRUM-359 | Optimize

## Authentication
Issue key | Summary | Issue Type | Status | Priority | Assignee | Created | Due date | Story Points | Sprint | Parent Key | Parent Summary
SCRUM-2 | Authentication | Epic | In Progress | High |  | 2025-11-17 | 2026-02-27
SCRUM-249 | CRUD | Task | Done | Highest | Thiraphat Panthong | 2026-01-12 | 2026-01-13 |  | SCRUM Sprint 1 | SCRUM-2 | Authentication
SCRUM-17 | User Account & Identity Model | Task | Done | Highest | Thiraphat Panthong | 2025-11-17 | 2026-01-13 |  | SCRUM Sprint 2 | SCRUM-2 | Authentication
SCRUM-126 | Refresh Token Logic | Task | Done | Medium | Thiraphat Panthong | 2025-12-18 | 2026-01-15 |  | SCRUM Sprint 2 | SCRUM-2 | Authentication
SCRUM-19 | Login & Signup Logic | Task | Done | High | Thiraphat Panthong | 2025-11-17 | 2026-01-15 |  | SCRUM Sprint 2 | SCRUM-2 | Authentication
SCRUM-130 | Password management | Task | Done | High | Thiraphat Panthong | 2025-12-18 | 2026-01-23 |  | SCRUM Sprint 2 | SCRUM-2 | Authentication
SCRUM-129 | Forgot Password Workflow | Task | Done | Highest | Thiraphat Panthong | 2025-12-18 | 2026-01-23 |  | SCRUM Sprint 2 | SCRUM-2 | Authentication
SCRUM-18 | Email Verification | Task | Done | Highest | Thiraphat Panthong | 2025-11-17 | 2026-01-23 |  | SCRUM Sprint 2 | SCRUM-2 | Authentication
SCRUM-132 | Role-Based Access Control | Task | Done | High | Thiraphat Panthong | 2025-12-18 | 2026-02-15 |  | SCRUM Sprint 2 | SCRUM-2 | Authentication
SCRUM-131 | Login Rate Limiting | Task | Done | Medium | Thiraphat Panthong | 2025-12-18 | 2026-02-15 |  | SCRUM Sprint 2 | SCRUM-2 | Authentication
SCRUM-269 | Session & Token Management | Task | Done | High | Nattapat Suwansipaisan | 2026-01-23 | 2026-02-17 |  | SCRUM Sprint 2 | SCRUM-2 | Authentication
SCRUM-275 | Multi-device Session Control | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-23 | 2026-02-12 |  | SCRUM Sprint 2 | SCRUM-269 | Session & Token Management
SCRUM-274 | Refresh Token Logic | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-23 | 2026-02-16 |  | SCRUM Sprint 2 | SCRUM-269 | Session & Token Management
SCRUM-273 | JWT Management | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-23 | 2026-02-16 |  | SCRUM Sprint 2 | SCRUM-269 | Session & Token Management
SCRUM-23 | Social Auth | Task | Done | Highest | Nattapat Suwansipaisan | 2025-11-17 | 2026-02-16 |  | SCRUM Sprint 2 | SCRUM-2 | Authentication
SCRUM-285 | Implementation Choosing(SDK vs. Manual) | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-23 | 2026-02-12 |  | SCRUM Sprint 2 | SCRUM-23 | Social Auth
SCRUM-272 | PKCE | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-23 | 2026-02-12 |  | SCRUM Sprint 2 | SCRUM-23 | Social Auth
SCRUM-271 | Handle Native Login State | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-23 | 2026-02-12 |  | SCRUM Sprint 2 | SCRUM-23 | Social Auth
SCRUM-268 | Account Linking Strategy | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-23 | 2026-02-12 |  | SCRUM Sprint 2 | SCRUM-23 | Social Auth
SCRUM-267 | User "Upsert" Logic | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-23 | 2026-02-12 |  | SCRUM Sprint 2 | SCRUM-23 | Social Auth
SCRUM-265 | With Google | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-23 | 2026-02-12 |  | SCRUM Sprint 2 | SCRUM-23 | Social Auth
SCRUM-264 | With Discord | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-23 | 2026-02-12 |  | SCRUM Sprint 2 | SCRUM-23 | Social Auth
SCRUM-133 | Protected Routes | Task | Done | Medium | Thiraphat Panthong | 2025-12-18 | 2026-02-19 |  | SCRUM Sprint 2 | SCRUM-2 | Authentication
SCRUM-327 | Learning path | Subtask | Done | Medium | Thiraphat Panthong | 2026-02-13 | 2026-02-16 |  | SCRUM Sprint 2 | SCRUM-133 | Protected Routes
SCRUM-326 | Reflection | Subtask | Done | Medium | Thiraphat Panthong | 2026-02-13 | 2026-02-16 |  | SCRUM Sprint 2 | SCRUM-133 | Protected Routes
SCRUM-325 | Authentication | Subtask | Done | Medium | Thiraphat Panthong | 2026-02-13 | 2026-02-16 |  | SCRUM Sprint 2 | SCRUM-133 | Protected Routes
SCRUM-310 | Admin | Task | To Do | Medium | Thiraphat Panthong | 2026-02-07 | 2026-03-06 |  | SCRUM Sprint 3 | SCRUM-2 | Authentication

## Recommendation
Issue key | Summary | Issue Type | Status | Priority | Assignee | Created | Due date | Story Points | Sprint | Parent Key | Parent Summary
SCRUM-6 | Recommendation | Epic | In Progress | High | Napadech | 2025-11-17 | 2026-03-10
SCRUM-37 | Data Pipeline | Task | In Progress | Medium | Napadech | 2025-11-17 | 2026-03-10 |  | SCRUM Sprint 3 | SCRUM-6 | Recommendation
SCRUM-313 | Design Flow (learning path) | Subtask | Done | Highest | Napadech | 2026-02-09 | 2026-02-09 |  | SCRUM Sprint 3 | SCRUM-37 | Data Pipeline
SCRUM-301 | Define Data Model | Subtask | Done | High | Napadech | 2026-02-06 | 2026-02-11 |  | SCRUM Sprint 3 | SCRUM-37 | Data Pipeline
SCRUM-259 | User Assessment Design | Subtask | Done | Highest | Napadech | 2026-01-21 | 2026-02-11 |  | SCRUM Sprint 3 | SCRUM-37 | Data Pipeline
SCRUM-282 | Define Algorithm | Subtask | Done | High | Napadech | 2026-01-23 | 2026-02-11 |  | SCRUM Sprint 3 | SCRUM-37 | Data Pipeline
SCRUM-262 | Strategy for New Users | Subtask | To Do | Highest | Napadech | 2026-01-21 | 2026-02-11 |  | SCRUM Sprint 3 | SCRUM-37 | Data Pipeline
SCRUM-281 | Feedback Loop Integration | Subtask | To Do | Medium | Napadech | 2026-01-23 | 2026-02-27 |  | SCRUM Sprint 3 | SCRUM-37 | Data Pipeline
SCRUM-280 | Strategy for Improve Model | Subtask | To Do | Medium | Napadech | 2026-01-23 | 2026-02-27 |  | SCRUM Sprint 3 | SCRUM-37 | Data Pipeline
SCRUM-279 | Storage to use | Subtask | To Do | High | Napadech | 2026-01-23 | 2026-02-13 |  | SCRUM Sprint 3 | SCRUM-37 | Data Pipeline
SCRUM-277 | Orchestrator | Subtask | To Do | High | Napadech | 2026-01-23 | 2026-02-13 |  | SCRUM Sprint 3 | SCRUM-37 | Data Pipeline
SCRUM-260 | Implement Interest Tagging | Subtask | To Do | Highest | Napadech | 2026-01-21 | 2026-02-11 |  | SCRUM Sprint 3 | SCRUM-37 | Data Pipeline
SCRUM-314 | implement full-pipeline | Subtask | To Do | Medium | Napadech | 2026-02-09 | 2026-02-27 |  | SCRUM Sprint 3 | SCRUM-37 | Data Pipeline
SCRUM-339 | Design Flow (home) | Subtask | To Do | Medium | Napadech | 2026-02-17 | 2026-02-27 |  | SCRUM Sprint 3 | SCRUM-37 | Data Pipeline
SCRUM-315 | Test full-pipeline | Subtask | To Do | Low | Napadech | 2026-02-09 | 2026-02-27 |  | SCRUM Sprint 3 | SCRUM-37 | Data Pipeline
SCRUM-352 | Integration to Home Reccomend | Task | To Do | Medium | Napadech | 2026-02-19 | 2026-03-10 |  | SCRUM Sprint 3 | SCRUM-6 | Recommendation
SCRUM-351 | Integration to Learning Path | Task | To Do | Medium | Napadech | 2026-02-19 | 2026-03-10 |  | SCRUM Sprint 3 | SCRUM-6 | Recommendation

## Social Learning
Issue key | Summary | Issue Type | Status | Priority | Assignee | Created | Due date | Story Points | Sprint | Parent Key | Parent Summary
SCRUM-7 | Social Learning | Epic | Done | Medium |  | 2025-11-17 | 2026-03-06
SCRUM-43 | Comment Display UI | Task | Done | Medium | Thiraphat Panthong | 2025-11-17 | 2026-02-25 |  | SCRUM Sprint 3 | SCRUM-7 | Social Learning
SCRUM-42 | Comment Creation | Task | Done | Medium | Nattapat Suwansipaisan | 2025-11-17 | 2026-03-02 |  | SCRUM Sprint 3 | SCRUM-7 | Social Learning
SCRUM-354 | Comment Reply | Task | Done | Medium | Nattapat Suwansipaisan |  | 2026-03-04 |  | SCRUM Sprint 3 | SCRUM-7 | Social Learning
SCRUM-355 | Mention base on username | Subtask | Done | Medium | Nattapat Suwansipaisan |  | 2026-03-04 |  | SCRUM Sprint 3 | SCRUM-354 | Comment Reply
SCRUM-356 | Mention base Display Full name | Subtask | Done | Medium | Thiraphat Panthong |  | 2026-03-04 |  | SCRUM Sprint 3 | SCRUM-354 | Comment Reply
SCRUM-353 | Comment Reaction | Task | Done | Medium | Thiraphat Panthong |  | 2026-03-04 |  | SCRUM Sprint 3 | SCRUM-7 | Social Learning
SCRUM-357 | Count reaction | Subtask | Done | Medium | Thiraphat Panthong |  | 2026-03-04 |  | SCRUM Sprint 3 | SCRUM-353 | Comment Reaction
SCRUM-358 | One person for count one action | Subtask | Done | Medium | Thiraphat Panthong |  | 2026-03-04 |  | SCRUM Sprint 3 | SCRUM-353 | Comment Reaction
SCRUM-44 | Edit & Delete Comment | Task | To Do | Medium | Thiraphat Panthong | 2025-11-17 | 2026-03-06 |  | SCRUM Sprint 3 | SCRUM-7 | Social Learning

## Dashboards
Issue key | Summary | Issue Type | Status | Priority | Assignee | Created | Due date | Story Points | Sprint | Parent Key | Parent Summary
SCRUM-5 | Dashboards | Epic | To Do | Medium |  | 2025-11-17 | 2026-03-27
SCRUM-28 | Student/Teacher Dashboard | Task | To Do | Medium | Amy Tripp | 2025-11-17 | 2026-03-11 |  | SCRUM Sprint 3 | SCRUM-5 | Dashboards
SCRUM-29 | Progress Visualization | Task | To Do | Medium | Amy Tripp | 2025-11-17 | 2026-03-17 |  | SCRUM Sprint 3 | SCRUM-5 | Dashboards
SCRUM-31 | Admin Overview Dashboard | Task | To Do | Medium | Amy Tripp | 2025-11-17 | 2026-03-22 |  | SCRUM Sprint 3 | SCRUM-5 | Dashboards
SCRUM-32 | Data Export | Task | To Do | Medium | Amy Tripp | 2025-11-17 | 2026-03-27 |  | SCRUM Sprint 3 | SCRUM-5 | Dashboards

## TEST
Issue key | Summary | Issue Type | Status | Priority | Assignee | Created | Due date | Story Points | Sprint | Parent Key | Parent Summary
SCRUM-30 | TEST | Epic | In Progress | Medium | Nattapat Suwansipaisan | 2025-11-17 | 2026-04-17
SCRUM-35 | Sprint 1 Testing | Test | Done | Highest | Nattapat Suwansipaisan | 2025-11-17 | 2026-01-21 |  | SCRUM Sprint 1 | SCRUM-30 | TEST
SCRUM-219 | Test design | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-04 | 2026-01-19 |  | SCRUM Sprint 1 | SCRUM-35 | Sprint 1 Testing
SCRUM-33 | Sprint 2 Testing | Test | Done | High | Nattapat Suwansipaisan | 2025-11-17 | 2026-02-19 |  | SCRUM Sprint 2 | SCRUM-30 | TEST
SCRUM-234 | Test design | Subtask | Done | Medium | Nattapat Suwansipaisan | 2026-01-05 | 2026-02-16 |  | SCRUM Sprint 2 | SCRUM-33 | Sprint 2 Testing
SCRUM-150 | API Testing | Subtask | Done | Medium | Nattapat Suwansipaisan | 2025-12-18 | 2026-02-19 |  | SCRUM Sprint 2 | SCRUM-33 | Sprint 2 Testing
SCRUM-149 | Integration Testing | Subtask | Done | Medium | Nattapat Suwansipaisan | 2025-12-18 | 2026-02-19 |  | SCRUM Sprint 2 | SCRUM-33 | Sprint 2 Testing
SCRUM-34 | Sprint 3 Testing | Test | To Do | Low | Nattapat Suwansipaisan | 2025-11-17 | 2026-03-16 |  | SCRUM Sprint 3 | SCRUM-30 | TEST
SCRUM-235 | Test design | Subtask | To Do | Medium | Nattapat Suwansipaisan | 2026-01-05 |  |  | SCRUM Sprint 3 | SCRUM-34 | Sprint 3 Testing
SCRUM-153 | API Testing | Subtask | To Do | Medium |  | 2025-12-18 |  |  | SCRUM Sprint 3 | SCRUM-34 | Sprint 3 Testing
SCRUM-152 | Integration Testing | Subtask | To Do | Medium |  | 2025-12-18 |  |  | SCRUM Sprint 3 | SCRUM-34 | Sprint 3 Testing
SCRUM-151 | Unit Testing | Subtask | To Do | Medium |  | 2025-12-18 |  |  | SCRUM Sprint 3 | SCRUM-34 | Sprint 3 Testing
SCRUM-36 | Sprint 4 Testing | Test | To Do | Lowest | Nattapat Suwansipaisan | 2025-11-17 | 2026-04-17 |  | SCRUM Sprint 4 | SCRUM-30 | TEST
SCRUM-236 | Test design | Subtask | To Do | Medium | Nattapat Suwansipaisan | 2026-01-05 |  |  | SCRUM Sprint 4 | SCRUM-36 | Sprint 4 Testing
SCRUM-147 | End-to-End (E2E) Testing | Subtask | To Do | Medium |  | 2025-12-18 |  |  | SCRUM Sprint 4 | SCRUM-36 | Sprint 4 Testing

## Deploy
Issue key | Summary | Issue Type | Status | Priority | Assignee | Created | Due date | Story Points | Sprint | Parent Key | Parent Summary
SCRUM-58 | Deploy | Epic | In Progress | Medium | Thiraphat Panthong | 2025-11-19 | 2026-04-17
SCRUM-317 | PoC with CI/CD and Azure | Task | Done | Medium | Thiraphat Panthong | 2026-02-11 | 2026-02-11 |  | SCRUM Sprint 2 | SCRUM-58 | Deploy
SCRUM-324 | Azure Portal Config | Subtask | Done | Medium | Thiraphat Panthong | 2026-02-11 | 2026-02-11 |  | SCRUM Sprint 2 | SCRUM-317 | PoC with CI/CD and Azure
SCRUM-323 | Setup DNS record | Subtask | Done | Medium | Thiraphat Panthong | 2026-02-11 | 2026-02-11 |  | SCRUM Sprint 2 | SCRUM-317 | PoC with CI/CD and Azure
SCRUM-322 | MailerSend | Subtask | Done | Medium | Thiraphat Panthong | 2026-02-11 | 2026-02-11 |  | SCRUM Sprint 2 | SCRUM-317 | PoC with CI/CD and Azure
SCRUM-321 | Domain Name | Subtask | Done | Medium | Thiraphat Panthong | 2026-02-11 | 2026-02-11 |  | SCRUM Sprint 2 | SCRUM-317 | PoC with CI/CD and Azure
SCRUM-320 | Setup Terraform | Subtask | Done | Medium | Thiraphat Panthong | 2026-02-11 | 2026-02-11 |  | SCRUM Sprint 2 | SCRUM-317 | PoC with CI/CD and Azure
SCRUM-319 | Set Secret Key in Reposity | Subtask | Done | Medium | Thiraphat Panthong | 2026-02-11 | 2026-02-11 |  | SCRUM Sprint 2 | SCRUM-317 | PoC with CI/CD and Azure
SCRUM-318 | GitHub Action to ACR | Subtask | Done | Medium | Thiraphat Panthong | 2026-02-11 | 2026-02-11 |  | SCRUM Sprint 2 | SCRUM-317 | PoC with CI/CD and Azure
SCRUM-59 | Last code review | Task | To Do | Medium | Thiraphat Panthong | 2025-11-19 | 2026-04-10 |  | SCRUM Sprint 4 | SCRUM-58 | Deploy
SCRUM-304 | Authentication | Subtask | To Do | Medium | Thiraphat Panthong | 2026-02-07 | 2026-02-18 |  | SCRUM Sprint 4 | SCRUM-59 | Last code review
SCRUM-303 | Learning Path | Subtask | To Do | Medium | Thiraphat Panthong | 2026-02-07 | 2026-02-18 |  | SCRUM Sprint 4 | SCRUM-59 | Last code review
SCRUM-302 | Reflection | Subtask | To Do | Medium | Thiraphat Panthong | 2026-02-07 | 2026-02-18 |  | SCRUM Sprint 4 | SCRUM-59 | Last code review

## _Data (hidden)
Sheet | SCRUM Key | SCRUM Number | Issue Type | Status
Reflection Tree | SCRUM-3 | 3 | Epic | Done
Reflection Tree | SCRUM-191 | 191 | Task | Done
Reflection Tree | SCRUM-13 | 13 | Task | Done
Reflection Tree | SCRUM-226 | 226 | Subtask | Done
Reflection Tree | SCRUM-225 | 225 | Subtask | Done
Reflection Tree | SCRUM-224 | 224 | Subtask | Done
Reflection Tree | SCRUM-223 | 223 | Subtask | Done
Reflection Tree | SCRUM-221 | 221 | Subtask | Done
Reflection Tree | SCRUM-220 | 220 | Subtask | Done
Reflection Tree | SCRUM-15 | 15 | Task | Done
Reflection Tree | SCRUM-230 | 230 | Subtask | Done
Reflection Tree | SCRUM-227 | 227 | Subtask | Done
Reflection Tree | SCRUM-233 | 233 | Subtask | Done
Reflection Tree | SCRUM-232 | 232 | Subtask | Done
Reflection Tree | SCRUM-231 | 231 | Subtask | Done
Reflection Tree | SCRUM-229 | 229 | Subtask | Done
Reflection Tree | SCRUM-228 | 228 | Subtask | Done
Reflection Tree | SCRUM-253 | 253 | Task | Done
Reflection Tree | SCRUM-238 | 238 | Task | Done
Reflection Tree | SCRUM-16 | 16 | Task | Done
Learning Path | SCRUM-1 | 1 | Epic | Done
Learning Path | SCRUM-193 | 193 | Task | Done
Learning Path | SCRUM-189 | 189 | Task | Done
Learning Path | SCRUM-208 | 208 | Subtask | Done
Learning Path | SCRUM-204 | 204 | Subtask | Done
Learning Path | SCRUM-203 | 203 | Subtask | Done
Learning Path | SCRUM-215 | 215 | Subtask | Done
Learning Path | SCRUM-207 | 207 | Subtask | Done
Learning Path | SCRUM-206 | 206 | Subtask | Done
Learning Path | SCRUM-205 | 205 | Subtask | Done
Learning Path | SCRUM-55 | 55 | Task | Done
Learning Path | SCRUM-196 | 196 | Subtask | Done
Learning Path | SCRUM-98 | 98 | Subtask | Done
Learning Path | SCRUM-93 | 93 | Subtask | Done
Learning Path | SCRUM-91 | 91 | Subtask | Done
Learning Path | SCRUM-90 | 90 | Subtask | Done
Learning Path | SCRUM-9 | 9 | Task | Done
Learning Path | SCRUM-100 | 100 | Subtask | Done
Learning Path | SCRUM-99 | 99 | Subtask | Done
Learning Path | SCRUM-248 | 248 | Subtask | Done
Learning Path | SCRUM-247 | 247 | Subtask | Done
Learning Path | SCRUM-245 | 245 | Subtask | Done
Learning Path | SCRUM-244 | 244 | Subtask | Done
Learning Path | SCRUM-243 | 243 | Subtask | Done
Learning Path | SCRUM-242 | 242 | Subtask | Done
Learning Path | SCRUM-239 | 239 | Task | Done
Learning Path | SCRUM-240 | 240 | Subtask | Done
Learning Path | SCRUM-252 | 252 | Subtask | Done
Learning Path | SCRUM-251 | 251 | Subtask | Done
Learning Path | SCRUM-115 | 115 | Task | Done
Learning Path | SCRUM-118 | 118 | Subtask | Done
Learning Path | SCRUM-117 | 117 | Subtask | Done
Learning Path | SCRUM-116 | 116 | Subtask | Done
Learning Path | SCRUM-10 | 10 | Task | Done
Learning Path | SCRUM-123 | 123 | Subtask | Done
Learning Path | SCRUM-122 | 122 | Subtask | Done
Learning Path | SCRUM-121 | 121 | Subtask | Done
Learning Path | SCRUM-120 | 120 | Subtask | Done
Learning Path | SCRUM-119 | 119 | Subtask | Done
Learning Path | SCRUM-11 | 11 | Task | Done
Learning Path | SCRUM-113 | 113 | Subtask | Done
Learning Path | SCRUM-112 | 112 | Subtask | Done
Learning Path | SCRUM-110 | 110 | Subtask | Done
Learning Path | SCRUM-109 | 109 | Subtask | Done
System design | SCRUM-8 | 8 | Epic | In Progress
System design | SCRUM-64 | 64 | Task | Done
System design | SCRUM-72 | 72 | Subtask | Done
System design | SCRUM-71 | 71 | Subtask | Done
System design | SCRUM-70 | 70 | Subtask | Done
System design | SCRUM-69 | 69 | Subtask | Done
System design | SCRUM-68 | 68 | Subtask | Done
System design | SCRUM-45 | 45 | Task | Done
System design | SCRUM-195 | 195 | Subtask | Done
System design | SCRUM-83 | 83 | Subtask | Done
System design | SCRUM-78 | 78 | Subtask | Done
System design | SCRUM-80 | 80 | Subtask | Done
System design | SCRUM-89 | 89 | Task | Done
System design | SCRUM-211 | 211 | Subtask | Done
System design | SCRUM-107 | 107 | Subtask | Done
System design | SCRUM-104 | 104 | Subtask | Done
System design | SCRUM-102 | 102 | Subtask | Done
System design | SCRUM-212 | 212 | Subtask | Done
System design | SCRUM-108 | 108 | Subtask | Done
System design | SCRUM-209 | 209 | Task | Done
System design | SCRUM-292 | 292 | Subtask | Done
System design | SCRUM-291 | 291 | Subtask | Done
System design | SCRUM-290 | 290 | Subtask | Done
System design | SCRUM-286 | 286 | Task | Done
System design | SCRUM-289 | 289 | Subtask | Done
System design | SCRUM-288 | 288 | Subtask | Done
System design | SCRUM-46 | 46 | Task | In Progress
System design | SCRUM-202 | 202 | Subtask | Done
System design | SCRUM-201 | 201 | Subtask | Done
System design | SCRUM-200 | 200 | Subtask | Done
System design | SCRUM-199 | 199 | Subtask | Done
System design | SCRUM-143 | 143 | Subtask | Done
System design | SCRUM-142 | 142 | Subtask | Done
System design | SCRUM-141 | 141 | Subtask | Done
System design | SCRUM-194 | 194 | Subtask | In Progress
System design | SCRUM-140 | 140 | Subtask | In Progress
System design | SCRUM-77 | 77 | Subtask | In Progress
System design | SCRUM-217 | 217 | Subtask | To Do
UX-UI | SCRUM-49 | 49 | Epic | In Progress
UX-UI | SCRUM-181 | 181 | Task | Done
UX-UI | SCRUM-186 | 186 | Subtask | Done
UX-UI | SCRUM-185 | 185 | Subtask | Done
UX-UI | SCRUM-184 | 184 | Subtask | Done
UX-UI | SCRUM-183 | 183 | Subtask | Done
UX-UI | SCRUM-51 | 51 | Task | In Progress
UX-UI | SCRUM-81 | 81 | Subtask | Done
UX-UI | SCRUM-92 | 92 | Subtask | Done
UX-UI | SCRUM-87 | 87 | Subtask | Done
UX-UI | SCRUM-84 | 84 | Subtask | Done
UX-UI | SCRUM-88 | 88 | Subtask | Done
UX-UI | SCRUM-94 | 94 | Subtask | Done
UX-UI | SCRUM-250 | 250 | Subtask | Done
UX-UI | SCRUM-86 | 86 | Subtask | Done
UX-UI | SCRUM-85 | 85 | Subtask | Done
UX-UI | SCRUM-95 | 95 | Subtask | Done
UX-UI | SCRUM-96 | 96 | Subtask | Done
UX-UI | SCRUM-300 | 300 | Subtask | Done
UX-UI | SCRUM-299 | 299 | Subtask | Done
UX-UI | SCRUM-298 | 298 | Subtask | Done
UX-UI | SCRUM-293 | 293 | Subtask | Done
UX-UI | SCRUM-346 | 346 | Subtask | Done
UX-UI | SCRUM-297 | 297 | Subtask | Done
UX-UI | SCRUM-296 | 296 | Subtask | Done
UX-UI | SCRUM-82 | 82 | Subtask | Done
UX-UI | SCRUM-75 | 75 | Subtask | Done
UX-UI | SCRUM-347 | 347 | Subtask | To Do
UX-UI | SCRUM-50 | 50 | Task | In Progress
UX-UI | SCRUM-74 | 74 | Subtask | Done
UX-UI | SCRUM-155 | 155 | Subtask | Done
UX-UI | SCRUM-168 | 168 | Subtask | Done
UX-UI | SCRUM-165 | 165 | Subtask | Done
UX-UI | SCRUM-164 | 164 | Subtask | Done
UX-UI | SCRUM-163 | 163 | Subtask | Done
UX-UI | SCRUM-162 | 162 | Subtask | Done
UX-UI | SCRUM-169 | 169 | Subtask | Done
UX-UI | SCRUM-175 | 175 | Subtask | Done
UX-UI | SCRUM-174 | 174 | Subtask | Done
UX-UI | SCRUM-172 | 172 | Subtask | Done
UX-UI | SCRUM-171 | 171 | Subtask | Done
UX-UI | SCRUM-170 | 170 | Subtask | Done
UX-UI | SCRUM-179 | 179 | Subtask | Done
UX-UI | SCRUM-178 | 178 | Subtask | Done
UX-UI | SCRUM-177 | 177 | Subtask | Done
UX-UI | SCRUM-176 | 176 | Subtask | Done
UX-UI | SCRUM-167 | 167 | Subtask | Done
UX-UI | SCRUM-166 | 166 | Subtask | Done
UX-UI | SCRUM-160 | 160 | Subtask | Done
UX-UI | SCRUM-159 | 159 | Subtask | Done
UX-UI | SCRUM-158 | 158 | Subtask | Done
UX-UI | SCRUM-156 | 156 | Subtask | Done
UX-UI | SCRUM-330 | 330 | Subtask | Done
UX-UI | SCRUM-349 | 349 | Subtask | Done
UX-UI | SCRUM-173 | 173 | Subtask | Done
UX-UI | SCRUM-154 | 154 | Subtask | Done
UX-UI | SCRUM-157 | 157 | Subtask | To Do
UX-UI | SCRUM-350 | 350 | Subtask | To Do
UX-UI | SCRUM-52 | 52 | Task | In Progress
UX-UI | SCRUM-294 | 294 | Subtask | Done
UX-UI | SCRUM-295 | 295 | Subtask | Done
UX-UI | SCRUM-344 | 344 | Subtask | Done
UX-UI | SCRUM-342 | 342 | Subtask | Done
UX-UI | SCRUM-341 | 341 | Subtask | Done
UX-UI | SCRUM-340 | 340 | Subtask | Done
UX-UI | SCRUM-338 | 338 | Subtask | Done
UX-UI | SCRUM-337 | 337 | Subtask | Done
UX-UI | SCRUM-336 | 336 | Subtask | Done
UX-UI | SCRUM-348 | 348 | Subtask | To Do
UX-UI | SCRUM-345 | 345 | Subtask | To Do
UX-UI | SCRUM-343 | 343 | Subtask | To Do
UX-UI | SCRUM-311 | 311 | Task | To Do
UX-UI | SCRUM-329 | 329 | Subtask | To Do
UX-UI | SCRUM-312 | 312 | Subtask | To Do
UX-UI | SCRUM-57 | 57 | Task | To Do
UX-UI | SCRUM-53 | 53 | Task | To Do
UX-UI | SCRUM-334 | 334 | Subtask | To Do
UX-UI | SCRUM-333 | 333 | Subtask | To Do
UX-UI | SCRUM-332 | 332 | Subtask | To Do
UX-UI | SCRUM-331 | 331 | Subtask | To Do
UX-UI | SCRUM-56 | 56 | Task | To Do
UX-UI | SCRUM-335 | 335 | Subtask | To Do
UX-UI | SCRUM-328 | 328 | Subtask | To Do
TEST | SCRUM-30 | 30 | Epic | In Progress
TEST | SCRUM-35 | 35 | Test | Done
TEST | SCRUM-219 | 219 | Subtask | Done
TEST | SCRUM-33 | 33 | Test | Done
TEST | SCRUM-234 | 234 | Subtask | Done
TEST | SCRUM-150 | 150 | Subtask | Done
TEST | SCRUM-149 | 149 | Subtask | Done
TEST | SCRUM-34 | 34 | Test | To Do
TEST | SCRUM-235 | 235 | Subtask | To Do
TEST | SCRUM-153 | 153 | Subtask | To Do
TEST | SCRUM-152 | 152 | Subtask | To Do
TEST | SCRUM-151 | 151 | Subtask | To Do
TEST | SCRUM-36 | 36 | Test | To Do
TEST | SCRUM-236 | 236 | Subtask | To Do
TEST | SCRUM-147 | 147 | Subtask | To Do
Authentication | SCRUM-2 | 2 | Epic | In Progress
Authentication | SCRUM-249 | 249 | Task | Done
Authentication | SCRUM-17 | 17 | Task | Done
Authentication | SCRUM-126 | 126 | Task | Done
Authentication | SCRUM-19 | 19 | Task | Done
Authentication | SCRUM-130 | 130 | Task | Done
Authentication | SCRUM-129 | 129 | Task | Done
Authentication | SCRUM-18 | 18 | Task | Done
Authentication | SCRUM-132 | 132 | Task | Done
Authentication | SCRUM-131 | 131 | Task | Done
Authentication | SCRUM-269 | 269 | Task | Done
Authentication | SCRUM-275 | 275 | Subtask | Done
Authentication | SCRUM-274 | 274 | Subtask | Done
Authentication | SCRUM-273 | 273 | Subtask | Done
Authentication | SCRUM-23 | 23 | Task | Done
Authentication | SCRUM-285 | 285 | Subtask | Done
Authentication | SCRUM-272 | 272 | Subtask | Done
Authentication | SCRUM-271 | 271 | Subtask | Done
Authentication | SCRUM-268 | 268 | Subtask | Done
Authentication | SCRUM-267 | 267 | Subtask | Done
Authentication | SCRUM-265 | 265 | Subtask | Done
Authentication | SCRUM-264 | 264 | Subtask | Done
Authentication | SCRUM-133 | 133 | Task | Done
Authentication | SCRUM-327 | 327 | Subtask | Done
Authentication | SCRUM-326 | 326 | Subtask | Done
Authentication | SCRUM-325 | 325 | Subtask | Done
Authentication | SCRUM-310 | 310 | Task | To Do
Recommendation | SCRUM-6 | 6 | Epic | In Progress
Recommendation | SCRUM-37 | 37 | Task | In Progress
Recommendation | SCRUM-313 | 313 | Subtask | Done
Recommendation | SCRUM-301 | 301 | Subtask | Done
Recommendation | SCRUM-259 | 259 | Subtask | Done
Recommendation | SCRUM-282 | 282 | Subtask | Done
Recommendation | SCRUM-262 | 262 | Subtask | To Do
Recommendation | SCRUM-281 | 281 | Subtask | To Do
Recommendation | SCRUM-280 | 280 | Subtask | To Do
Recommendation | SCRUM-279 | 279 | Subtask | To Do
Recommendation | SCRUM-277 | 277 | Subtask | To Do
Recommendation | SCRUM-260 | 260 | Subtask | To Do
Recommendation | SCRUM-314 | 314 | Subtask | To Do
Recommendation | SCRUM-339 | 339 | Subtask | To Do
Recommendation | SCRUM-315 | 315 | Subtask | To Do
Recommendation | SCRUM-352 | 352 | Task | To Do
Recommendation | SCRUM-351 | 351 | Task | To Do
Social Learning | SCRUM-7 | 7 | Epic | Done
Social Learning | SCRUM-43 | 43 | Task | Done
Social Learning | SCRUM-42 | 42 | Task | Done
Social Learning | SCRUM-44 | 44 | Task | To Do
Social Learning | SCRUM-354 | 354 | Task | Done
Social Learning | SCRUM-355 | 355 | Subtask | Done
Social Learning | SCRUM-356 | 356 | Subtask | Done
Social Learning | SCRUM-353 | 353 | Task | Done
Social Learning | SCRUM-357 | 357 | Subtask | Done
Social Learning | SCRUM-358 | 358 | Subtask | Done
Deploy | SCRUM-58 | 354 | Epic | In Progress
Deploy | SCRUM-317 | 355 | Task | Done
Deploy | SCRUM-324 | 356 | Subtask | Done
Deploy | SCRUM-323 | 353 | Subtask | Done
Deploy | SCRUM-322 | 357 | Subtask | Done
Deploy | SCRUM-321 | 358 | Subtask | Done
Deploy | SCRUM-320 | 58 | Subtask | Done
Deploy | SCRUM-319 | 317 | Subtask | Done
Deploy | SCRUM-318 | 324 | Subtask | Done
Deploy | SCRUM-59 | 323 | Task | To Do
Deploy | SCRUM-304 | 322 | Subtask | To Do
Deploy | SCRUM-303 | 321 | Subtask | To Do
Deploy | SCRUM-302 | 320 | Subtask | To Do
Dashboards | SCRUM-5 | 319 | Epic | To Do
Dashboards | SCRUM-28 | 318 | Task | To Do
Dashboards | SCRUM-29 | 59 | Task | To Do
Dashboards | SCRUM-31 | 304 | Task | To Do
Dashboards | SCRUM-32 | 303 | Task | To Do

## _Lists (hidden)
Parent Summary | Reporter | Assignee | Sprint
AI Insight Analysis | Amy Tripp | Amy Tripp | SCRUM Sprint 1
API Design | Napadech | Napadech | SCRUM Sprint 2
Admin Page | Nutgritta Prasomthongsuk | Nattapat Suwansipaisan | SCRUM Sprint 3
Authentication | Thiraphat Panthong | Nutgritta Prasomthongsuk | SCRUM Sprint 4
Authentication Pages |  | Thiraphat Panthong
Collection Learning Path
Component-Widget
Dashboard Layout
Dashboards
Data Pipeline
Database Design
Deploy
History System
Infrastructure Set
Integrate system (Deploy)
Landing Page
Last code review
Learning Path
Learning Path Page Layout
Logs Design
Path Generator
PoC with CI/CD and Azure
Progress Visualization
Protected Routes
Recommendation
Reflection Entry
Reflection Page Layout
Reflection Tree
Resume System
Sample data
Search Learning Path
Search System Template
Session & Token Management
Social Auth
Social Learning
Sprint 1 Testing
Sprint 2 Testing
Sprint 3 Testing
Sprint 4 Testing
System design
TEST
UX/UI